## Slide 1
TechCorp IAM Platform
Implementation Plan
Roadmap for integrating user lifecycle management and access controls across enterprise systems
Tata Cybersecurity Job Simulation | Platform Integration
IAM
HR Data
Directory
Cloud Apps
Plain meaning: this plan explains how TechCorp will connect IAM to HR, directories, legacy apps, third-party tools and cloud services.

## Slide 2
Implementation objective
Move from IAM design to a secure, scalable platform rollout.
1
Prepare
Confirm scope, systems, roles and owners
2
Integrate
Connect HR, directory, apps and cloud
3
Secure
Apply RBAC, MFA, SSO and privileged controls
4
Validate
Pilot, test access flows and fix gaps
5
Scale
Roll out globally and monitor continuously
Core idea
The IAM platform should become the control point for identity, authentication, authorisation and access changes across TechCorp.
Plain meaning: before users can access systems, IAM should confirm who they are and what they are allowed to use.

## Slide 3
12-week implementation roadmap
A phased rollout reduces risk and makes integration easier to control.
Weeks 1–2
Discovery & planning
Confirm apps, users, roles, risk, owners
Weeks 3–4
Platform setup
Configure IAM tenant, directory links, admin roles
Weeks 5–7
Core integrations
Connect HR, AD, SSO, MFA, key apps and cloud
Weeks 8–9
Pilot & testing
Test Joiner-Mover-Leaver, RBAC, access requests
Weeks 10–11
Rollout
Deploy by business unit and migrate priority apps
Week 12+
Operate & improve
Monitor logs, reviews, reports and optimisation
Plain meaning: do not connect everything at once. Start with planning, integrate priority systems, test, then scale.

## Slide 4
Target integration architecture
IAM sits between identity sources and enterprise resources.
HR System
(employee status)
Active Directory /
Identity Store
IAM Platform
Provisioning • RBAC
SSO • MFA • Audit
Legacy Apps
Third-party Apps
Cloud Services
SOC / SIEM Logs
Access decisions and identity changes flow through IAM before users reach business systems.
Plain meaning: IAM connects to HR for employee changes, to directories for identities, and to apps/cloud for access control.

## Slide 5
Integration challenges and mitigations
The plan must handle old systems, external applications and cloud access securely.
Challenge
Risk
Mitigation
Legacy systems
Older apps may not support modern SSO or APIs
Use connectors, phased migration and manual controls where automation is not possible
Third-party apps
Different authentication standards and vendor limits
Use SAML/OIDC where supported; document exceptions and monitor access
Cloud services
Multiple cloud identities can create inconsistent permissions
Centralise access through IAM, enforce MFA and standard cloud roles
Data quality
Incorrect HR or role data can give wrong access
Clean role data before rollout; test Joiner-Mover-Leaver flows
User adoption
Employees may resist new login processes
Communicate early, train users, pilot first, then roll out gradually
Plain meaning: successful IAM is not just buying a tool. The difficult part is connecting many systems safely.

## Slide 6
Resources, ownership and milestones
Clear responsibilities help the IAM rollout stay controlled.
Project sponsor
Approves scope, budget and business priorities
IAM team
Configures platform, roles, SSO, MFA and governance
HR team
Provides employee data and lifecycle triggers
IT / app owners
Support integration with legacy and business applications
Security / SOC
Reviews logs, suspicious access and incident response links
Change management
Communication, training and user support
Key milestone: pilot group successfully completes onboarding, role change and offboarding tests before wider rollout.
Plain meaning: IAM needs HR, IT, security and business teams working together, not only the cybersecurity team.

## Slide 7
Alignment with business goals
The implementation supports security, efficiency and user experience.
Enhance cybersecurity
MFA for sensitive access
Least privilege and RBAC
Audit logs for investigations
Streamline operations
Automated provisioning
Faster onboarding
Fewer manual access tickets
Improve user experience
SSO across approved apps
Self-service access requests
Clear approvals and status tracking
Success measures
Reduced onboarding time • fewer orphaned accounts • higher MFA coverage • regular access review completion • cleaner SOC visibility into identity events
Plain meaning: the IAM project should produce visible security and business improvements, not just a new platform.

## Slide 8
Recommended implementation approach
Start controlled, prove the process, then scale globally.
1
Prioritise HR, directory, SSO and MFA integrations first because they control identity creation and authentication.
2
Use RBAC and least privilege to standardise access, then test Joiner-Mover-Leaver processes with a pilot group.
3
Roll out by business unit, monitor identity events, review access regularly and improve the platform over time.
Outcome: secure access, faster operations and clearer visibility for security monitoring.
Plain meaning: this is a careful rollout plan, not an overnight switch.